## Product Backlog
Product Backlog
Epic, feature, requirement | Story ID | User Story | Story Points | Owner | Sprint
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | For example, 1-2 means the second sprint in the first stream of sprints
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 5 | Consultant | 1-2
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  | "Define project scope" → Sprint 1-1 (initial planning)
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 |  | "Identify target audience" → Sprint 1-2 (follows market research)
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3 |  | "Set up recording equipment" → Sprint 2-2 (technical execution)
"Create a launch campaign" → Sprint 2-3 (final phase)
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 8 | Alina | 2-2
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 5 | Bailey | 2-3
Note that product backlog entries (in Column A) are granularized as they move up, so not all entries in Column A will initially be broken down into user stories. This decomposition into user stories may happen after sprints have begun. You can adjust the number and type of entries in all the columns to your project needs. For example, you could have three instead of four user stories for Epic 001.

## Sprint 1-1
PRODUCT BACKLOG AFTER THIS SPRINT STARTS | [6 empty] | Sprint Backlog
Epic, feature, requirement | Story ID | Story | Story Points | Owner | Sprint |  | Sprint 1-1 (first sprint in first stream of sprints)
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1 |  | Definition of Done: The Project Scope document is drafted and reviewed by all stakeholders. Market research surveys are completed and summarized into a report. The target audience profile is identified with supporting data.
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | ID | User Story | Tasks | Owner | Status | Story Points | Actual Cost | Planned Cost (1k/SP) | ACTUAL | CUMULATIVE Story points | Cumulative Planned Cost | Cumulative Actual Cost
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 5 | Consultant | 1-2 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | Task 1: Research project requirements | Alina (Project Manager) | Complete | 3 | 2700 | 3000 | Week 1 | 16 | 16000 | 8200
[8 empty] | Task 2: Identify stakeholders | Dwayne (Core Team) | Complete | 3 | 2500 | 3000 | Week 2 | 24 | 24000 | 18400
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  |  | Task 3: Draft initial scope document | Consultant 1 | Complete | 3 | 3400 | 3000 | Week 3 | 32 | 32000 | 32550
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 |  |  | Task 4: Review scope with team | Consultant 2 | Complete | 3 | 3100 | 3000 | Total | 40 | 40000 | 40650
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3 |  |  | Task 5: Finalize scope | Project Manager | Complete | 3 | 3200 | 3000
[12 empty] | 14900 | 15000 | Average velocity for this stream = |  | 10
[6 empty] | US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | Task 1: Identify target audience | Bailey (Core Team) | Complete | 5 | 5500 | 5000
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1 |  |  | Task 2: Analyze competitor trends | Amulya (Marketing) | Complete | 5 | 4300 | 5000
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1 |  |  | Task 3: Conduct surveys | Choua (Communications) | Complete | 5 | 5050 | 5000
[8 empty] | Task 4: Review data and insights | Bob (Core Team) | Complete | 5 | 6000 | 5000
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 8 | Alina | 2-2 |  |  | Task 5: Create final market research report | Jessica (Core Team) | Complete | 5 | 4900 | 5000
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 5 | Bailey | 2-3 | [6 empty] | 25750 | 25000
[8 empty] | Total Planned Sprint Story Points = |  |  | 40
[9 empty] | Total Planned Cost of Sprint = |  | 40000
[9 empty] | Total Actual Cost of Sprint = |  | 40650

## Sprint 1-2
PRODUCT BACKLOG AFTER THIS SPRINT STARTS | [6 empty] | Sprint Backlog
Epic, feature, requirement | Story ID | Story | Story Points | Owner | Sprint |  | Sprint 1-2 (second sprint in first stream of sprints)
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1 |  | Definition of Done: Audience segmentation analysis is completed and validated with research data. A final audience persona document is ready for content planning. Podcast format options are compared and the best format is selected with justification.
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | ID | User Story | Tasks | Owner | Status | Story Points | Actual Cost | Planned Cost (1k/SP) |  | ACTUAL | CUMULATIVE Story points | Cumulative Planned Cost | Cumulative Actual Cost
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 4 | Consultant | 1-2 | US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy | Task 1: Conduct audience segmentation | Alina (Core Team) | Complete | 4 | 4200 | 4000 |  | Week 1 | 7 | 7000 | 6900
[8 empty] | Task 2: Analyze demographics & behaviors | Consultant 1 | Complete | 4 | 3900 | 4000 |  | Week 2 | 14 | 14000 | 13700
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  |  | Task 3: Create audience persona profiles | Consultant 2 | In-Progress | 4 | 2000 | 4000 |  | Week 3 | 17 | 17000 | 15700
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 | [9 empty] | Total | 21 | 21000 | 16700
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3
[12 empty] | 10100 | 12000 | Average velocity for this stream = |  |  | 5.25
[6 empty] | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | Task 1: Research existing podcast formats | Bailey (Core Team) | Complete | 3 | 2700 | 3000
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1 |  |  | Task 2: Compare format suitability | Bob (Core Team) | Complete | 3 | 2900 | 3000
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1 |  |  | Task 3: Choose the final format | Bailey (Core Team) | In-Progress | 3 | 1000 | 3000
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 6 | Alina | 2-2
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 5 | Bailey | 2-3 | [6 empty] | 6600 | 9000
[8 empty] | Total Planned Sprint Story Points = |  |  | 21
[8 empty] | Total Planned Cost of Sprint = |  | 21000
[8 empty] | Total Actual Cost of Sprint = |  | 16700

## Sprint 1-3
PRODUCT BACKLOG AFTER THIS SPRINT STARTS | [6 empty] | Sprint Backlog
Epic, feature, requirement | Story ID | Story | Story Points | Owner | Sprint |  | Sprint 1-3 (third sprint in first stream of sprints)
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1 |  | Definition of Done: A structured episode topic plan is created for at least 5 episodes. Industry research confirms that topics align with audience interest. Episode script templates are drafted, reviewed, and approved by the content team.
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | ID | User Story | Tasks | Owner | Status | Story Points |  | ACTUAL | CUMULATIVE Story points | Cumulative Planned Cost | Cumulative Actual Cost
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 4 | Consultant | 1-2 | US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | Task 1: Brainstorm potential episode topics | Alina (Core Team) | Not Started | 12 |  | Week 1 | 12 | 12000 | 0
[8 empty] | Task 2: Research trending topics in the industry | Consultant 1 | Not Started | 10 |  | Week 2 | 30 | 30000 | 0
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  |  | Task 3: Categorize topics into thematic seasons | Consultant 2 | Not Started | 6 |  | Week 3 | 38 | 38000 | 0
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 | [7 empty] | Total | 52 | 52000 | 0
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3
[12 empty] | Average velocity for this stream = |  |  | 17.3333
[6 empty] | US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | Task 1: Develop episode structure templates | Bailey (Core Team) | Not Started | 8
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1 |  |  | Task 2: Write draft scripts for first episodes | Bob (Core Team) | Not Started | 8
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1 |  |  | Task 3: Review and refine scripts for engagement | Consultant 2 | Not Started | 8
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 6 | Alina | 2-2
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 4 | Bailey | 2-3
[8 empty] | Total Planned Sprint Story Points = |  |  | 52

## Sprint 2-1
PRODUCT BACKLOG AFTER THIS SPRINT STARTS | [6 empty] | Sprint Backlog
Epic, feature, requirement | Story ID | Story | Story Points | Owner | Sprint |  | Sprint 2-1 (first sprint in second stream of sprints)
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1 |  | Definition of Done: All necessary recording equipment is selected and purchased. Software is installed and tested for compatibility with recording setup. Audio quality checks confirm acceptable sound levels and clarity.
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | ID | User Story | Tasks | Owner | Status | Story Points | Actual Cost | Planned Cost (1k/SP) |  | ACTUAL | CUMULATIVE Story points | Cumulative Planned Cost | Cumulative Actual Cost
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 5 | Consultant | 1-2 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | Task 1: Research and select recording equipment | John | Complete | 8 | 7900 | 8000 |  | Week 1 | 8 | 8000 | 12400
[8 empty] | Task 2: Purchase and set up recording devices | Jack | Complete | 8 | 7000 | 8000 |  | Week 2 | 21 | 21000 | 25000
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  |  | Task 3: Test equipment for audio quality | Emily | Complete | 8 | 8100 | 8000 |  | Week 3 | 29 | 29000 | 33100
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 | [9 empty] | Total | 39 | 39000 | 38000
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3
[12 empty] | 23000 | 24000 | Average velocity for this stream = |  |  | 9.75
[6 empty] | US008 | As a technician, I want to test the recording software so that we avoid technical issues. | Task 1: Research suitable recording software | Bailey (Core Team) | Complete | 5 | 4500 | 5000
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1 |  |  | Task 2: Install and configure software | Consultant 2 | Complete | 5 | 5600 | 5000
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1 |  |  | Task 3: Perform test recordings and troubleshoot | Consultant 1 | Complete | 5 | 4900 | 5000
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 8 | Alina | 2-2
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 5 | Bailey | 2-3 | [6 empty] | 15000 | 15000
[8 empty] | Total Planned Sprint Story Points = |  |  | 39
[8 empty] | Total Planned Cost of Sprint = |  | 39000
[8 empty] | Total Actual Cost of Sprint = |  | 38000

## Sprint 2-2
PRODUCT BACKLOG AFTER THIS SPRINT STARTS | [6 empty] | Sprint Backlog
Epic, feature, requirement | Story ID | Story | Story Points | Owner | Sprint |  | Sprint 2-2 (second sprint in second stream of sprints)
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1 |  | Definition of Done: A marketing strategy document is drafted, reviewed, and finalized. Promotional content drafts are created and scheduled for review. The podcast launch timeline is confirmed with key dates and milestones.
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | ID | User Story | Tasks | Owner | Status | Story Points | Actual Cost | Planned Cost (1k/SP) |  | ACTUAL | CUMULATIVE Story points | Cumulative Planned Cost | Cumulative Actual Cost
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 4 | Consultant | 1-2 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | Task 1: Develop marketing strategy | Alina (Core Team) | Complete | 6 | 5900 | 6000 |  | Week 1 | 0 | 0 | 5900
[8 empty] | Task 2: Create promotional content | Bailey (Core Team) | Complete | 6 | 7000 | 6000 |  | Week 2 | 6 | 6000 | 12900
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  |  | Task 3: Plan campaign launch timeline | Consultant 1 | Complete | 6 | 4900 | 6000 |  | Week 3 | 12 | 12000 | 17800
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 | [9 empty] | Total | 18 | 18000 | 17800
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3
[12 empty] | 17800 | 18000 | Average velocity for this stream = |  |  | 4.5
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 6 | Alina | 2-2
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 5 | Bailey | 2-3 | [6 empty] | 0 | 0
[8 empty] | Total Planned Sprint Story Points = |  |  | 18
[8 empty] | Total Planned Cost of Sprint = |  | 18000
[8 empty] | Total Actual Cost of Sprint = |  | 17800

## Sprint 2-3
PRODUCT BACKLOG AFTER THIS SPRINT STARTS | [6 empty] | Sprint Backlog
Epic, feature, requirement | Story ID | Story | Story Points | Owner | Sprint |  | Sprint 2-3 (third sprint in second stream of sprints)
Epic 001 | US001 | As a project manager, I want to define the project scope so that all stakeholders are aligned. | 3 | Alina | 1-1 |  | Definition of Done: The social media content calendar is fully planned. Promotional designs are completed and approved by the marketing team. All promotional posts are scheduled across multiple platforms.
| US002 | As a marketer, I want to conduct market research so that I can identify audience preferences. | 5 | Bailey | 1-1 | ID | User Story | Tasks | Owner | Status | Story Points |  | ACTUAL | CUMULATIVE Story points | Cumulative Planned Cost | Cumulative Actual Cost
| US003 | As a researcher, I want to identify the target audience so that we can refine our content strategy. | 4 | Consultant | 1-2 | US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | Task 1: Plan social media content calendar | Bailey (Core Team) | Not Started | 4 |  | Week 1 | 0 | 0 | 0
[8 empty] | Task 2: Design promotional posts | Choua (Communications) | Not Started | 4 |  | Week 2 | 4 | 4000 | 0
Requirement 002 | US004 | As a producer, I want to select a podcast format so that we maintain consistency. | 3 | Bailey | 1-2 |  |  | Task 3: Schedule posts on multiple platforms | Amulya (Marketing) | Not Started | 4 |  | Week 3 | 8 | 8000 | 0
| US005 | As a content strategist, I want to define podcast topics so that we have a structured content plan. | 5 | Alina | 1-3 | [7 empty] | Week 4 | 12 | 12000 | 0
| US006 | As a scriptwriter, I want to draft episode scripts so that recordings are efficient and engaging. | 8 | Consultant | 1-3
[12 empty] | Average velocity for this stream = |  |  | 4
Feature 003 | US007 | As an audio engineer, I want to set up recording equipment so that we achieve high-quality sound. | 8 | Varun | 2-1
| US008 | As a technician, I want to test the recording software so that we avoid technical issues. | 5 | Bailey | 2-1
Requirement 004 | US009 | As a marketing lead, I want to create a launch campaign so that we can build an audience. | 6 | Alina | 2-2
| US010 | As a social media manager, I want to schedule promotional posts so that we engage our audience. | 4 | Bailey | 2-3
[8 empty] | Total Planned Sprint Story Points = |  |  | 12

## Calculation
| Sprint 1-1 | Sprint 1-2 | Sprint 1-3 | Sprint 2-1 | Sprint 2-2 | Sprint 2-3 | Total
Planned SP | 40 | 21 | 52 | 39 | 18 | 12 | 182
Completed SP | 40 | 14 | 0 | 39 | 18 | 0 | 111
Planned Cost | 40000 | 21000 | 52000 | 39000 | 18000 | 12000 | 182000
Actual Cost | 40650 | 16700 | 0 | 38000 | 17800 | 0 | 113150
Table is as of the end of Month 2
EV | 111000
AC | 113150
PV | 118000
CPI= | 0.981
SPI= | 0.94068
Explanation | Solution for cumulative planned cost and actual cost was cross-referenced with the weekly costs from the double S curve values.
Explanation | EV, AC, and PV were calculated from the planned cost, actual cost, planned story point, and actual story point completed in each Sprint during the first two months. Then, those values were used to calculate the CPI and SPI for the project at the end of month 2. The project is slightly behind schedule (SPI 0.94) due to task 3 in both US003 and US004 not being completed at the end of Sprint 1-2 (this was done deliverately to inject realism into the assignment.) The project is performing as expected or slightly worse than expected on cost at the end of month 2 (CPI 0.98) due mostly to Sprint 1-2 not being completed, while cost is running a little high for the 14 completed Story Points (this was also done deliberately to inject realism into the assignment.)

## Doube S Curve
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Cumulative Actual Cost | 20600 | 43400 | 65650 | 78650 | 91450 | 105250 | 112150 | 113150 | 113150 | 113150 | 113150 | 113150
Cumulative Planned Cost | 24000 | 45000 | 61000 | 79000 | 86000 | 99000 | 108000 | 118000 | 130000 | 152000 | 164000 | 182000
Current as of end of week | 8
Explanation | The Cumulative Actual Cost and Planned Cost per week (for precision) were calculated by extracting the data from the corresponding cell in each Sprint Sheet. Each Week includes the cost for the corresponding Story Points on the two simultaneous Sprints. These values were used to build a Double-S Curve Chart that shows the project largely fell within the planned budget up to week 8. The Cumulative Actual Cost line remains constart after week 8 because that is the "current as of" date.
Note | The assignment didn’t specify which Double-S Curve to make, so we decided to show the cumulative Planned vs Actual Cost chart.